## Sheet1
Task | estimated time (hrs) | owner
understand current Xmap schema and stored procedures | 8 | Ted
bring up test instance of Xmap database | 3 | Ted
map and implement current queries to exonmap stored procedures | 5 | Ted
testing | 5 | Ted
Integrate queries into package | 3 | Ted
documentation | 3 | Ted
bring up production instance of Xmap database | 8 | Sunita?